# SCRIPT 4 – How to Develop a Budget for Your Project

6–8 minutes | Spoken by Kaylie, Senior Funding Development Lead at Sector 3

Hi, I’m Kaylie, welcome back to our Introduction to Funding mini course.

In this video, we’ll take you through how to develop a simple and effective budget. We’ll look at how to:

- Start with clear calculations

- Research and gather quotes

- Avoid underselling yourself

- Consider the current economic context

- Cross‑check your final figures

The examples being used in this course relate to funding for English language classes, however the learning can be used by any organisation wishing to apply for any type of funding.

When you apply for funding, a clear and realistic budget is just as important as a strong project plan. Even if the funder doesn’t ask for a detailed breakdown at the start, having a well-prepared budget shows that you understand your project, the costs involved, and the difference it will make.

Let’s begin.

## Start with Calculations

Begin by creating a simple spreadsheet to list all your project costs. It doesn’t need to look fancy, it just needs to be accurate.

A good budget helps you:

- Understand what you need to deliver your project

- Explain your costs if a funder asks questions

- Stay consistent if you apply to several funders

- Plan ahead if you receive less funding than expected

Check what the funder will pay for

Before you start adding any numbers, make sure you understand exactly what the funder will and won’t cover. Every funder is different. Some will not pay for staff time, food, equipment, or core running costs like rent and heating. Others may only fund project costs and not everyday expenses.

If you ask for something the funder does not fund, it can risk your application, even if the rest of your project is very strong. So take time to read the guidance carefully, and make sure every cost you include is allowed. This saves time, avoids mistakes, and increases your chances of success.

## Research and Get Quotes

Research is essential. For anything expensive, try to collect at least three quotes so you can show you have looked at a fair price and you’re not guessing.

Funders may ask to see these quotes, so it’s useful to save them in a folder before you submit your application.

Also consider what might be provided for free. This could be:

- Donations from local businesses

- Free room hire from a community centre

- Equipment from a sponsorship scheme

When you list your costs, include everything you need for the project to run well, such as:

- Staff time or tutor costs

- Volunteer expenses (for example, travel or background checks)

- Learning materials and stationery

- Venue hire

- Refreshments, if needed

Try to avoid round numbers like “£100” or “£500” as they can look like guesses. Funders trust budgets more when the figures are specific.

## Don’t Undersell Yourself

Many groups worry that asking for too much will reduce their chances of success. But asking for too little can also cause problems.

Sometimes funders offer less than you requested. If you have already reduced your costs because you were trying to appear “reasonable,” you may not have enough to run the project properly.

It’s important to budget fairly for:

- Your staff or tutors

- Your volunteers

- The communities, cohorts or learners you support

For example, if you run ESOL classes, you can include:

- Teaching resources

- Notebooks and pens

- Teaching aids such as whiteboards or flashcards

- Printing costs

Volunteers should not be left out of pocket. Funders want to see that you are a responsible organisation that takes care of its team.

If the funder allows it, also include a fair proportion of your organisation’s overheads. These are real costs that keep your project going.

Overheads (or core costs) are the everyday running costs of your organisation, the things you need to keep your group going, even if you are not delivering a specific project at that moment. Examples of overheads include heating, electricity, phone or internet bills, insurance, stationery, or the time spent on administration. These costs keep your organisation open and functioning, and without them, you couldn’t deliver your activities. Funders will usually allow for an extra 10% of the budget to be included as overheads, but check with each funder in case they allow for more, less, or not at all.

Some funders like to see that you have approached more than one funder for support. This shows you are proactive and not relying on one single source of money.

## Factor in the Current Context

The world is changing quickly, and your budget needs to reflect that.

Consider factors such as:

- Rising energy and living costs

- Higher venue hire prices

- Increased travel costs

- Inflation - especially for projects lasting more than one year

Including these shows your budget is realistic and that your project will not struggle later because things became more expensive.

## Cross‑Check Everything

Before sending your application, take time to check:

- Your calculations are correct

- Your budget matches your project plan

- Your total budget matches the total you ask for on the form

- You haven’t included anything the funder does not cover

Sometimes the application form asks for the total cost in one place and the detailed budget in another. Make sure these match exactly.

A well‑checked budget gives funders confidence that you understand your project and can manage money responsibly.

## Extra Tips and Best Practice

Here are some final suggestions to make your budget even stronger:

### Break it down clearly

List each cost on its own line: staff costs, materials, venue hire, volunteer expenses. Avoid lump sums.

Essential costs

Make a list of everything you think you will need to run your activity, for example, the cost of hiring a venue, refreshments for people attending, any equipment you will need etc. Once you have a full list, make a note of which are essential, meaning you cannot run the activity without them. Anything else is considered a ‘want’ rather than a ‘need’. Depending on how much the funder will give, and what they will fund, you might be able to ask for everything on your budget. If not, you can have the essential ‘needs’ covered, and apply to other funders or raise money in other ways to cover the ‘wants’.

### Justify the cost

Briefly explain why each cost is needed.
 For example:
 “£50 for ESOL learning materials for 12 learners across 10 sessions.”

### Plan for unexpected changes

Prices can go up, or end up costing more than expected. Adding a small buffer shows good planning.

### Use tables or visual layouts

If the funder allows it, clear tables make the budget easier to understand.

### Keep your calculations

If a funder asks how you arrived at an amount, you can explain it clearly. This also helps when applying for other grants in future.

Closing Message

Think of your budget as part of your project’s story. It shows you have thought carefully about the needs of your community, the resources you require, and how you will deliver your work safely and effectively.

A strong budget is not just a list of numbers, it shows professionalism, preparation, and credibility. Take your time, research your costs, and be confident in asking for what you truly need.

A well‑planned budget could be the difference between a funded project and a missed opportunity.

Good luck and we’ll see you in the next part of our Introduction to Funding mini course: How to reach service users

For more resources and support, it’s worth contacting your Local Infrastructure Organisation, also known as a CVS, (Council for Voluntary Service). An LIO or CVS can provide support, resources and guidance for local community organisations.